## 1-Design Concept
Purpose: Assess whether the proposed concept is adequate enough to proceed toward detailed design and implementation.
Boundary: Focus on whether the concept can work in principle. Detailed validation, testing, and final design verification should be assessed under Design Verification.
Scoring rule: Use the current evidence and design maturity. Examples are provided to guide judgment, not to limit the evidence raters may consider.
Indicator | Guiding question | Example evidence
Concept feasibility | Can the concept physically meet the required performance and constraints? | Sizing, power balance, pressure/flow estimate, cavitation/material/thermal checks
Concept robustness | Can the concept tolerate expected uncertainty or off-nominal conditions? | Sensitivity analysis, margin assessment, inlet pressure/speed/temperature variation
Design expertise | Does the team have enough relevant expertise to develop the concept? | Prior experience, analysis/test capability, access to experts
Design-process discipline | Is the concept developed through a traceable design process? | Assumptions, trade studies, reviews, risk list, interface control, action tracking
Score | General meaning
0 — Fail | Not demonstrated or unacceptable
1 — Poor | Major concerns remain
2 — Adequate | Partially supported, but important gaps remain
3 — Good | Supported with manageable concerns
4 — Excellent | Strongly supported for current maturity
Concept Feasibility
Guiding question: Can the concept physically meet required performance and constraints?
Example evidence | Sizing, power balance, pressure/flow estimate, cavitation/material/thermal checks
Score | Example interpretation
0 — Fail | Violates known physical or material limits.
1 — Poor | Major feasibility issue may require concept change.
2 — Adequate | Plausible, but key assumptions are unclear.
3 — Good | Current analysis supports feasibility; concerns are manageable.
4 — Excellent | Key analyses are consistent; no major risk is identified.
Concept Robustness
Guiding question: Can the concept tolerate expected uncertainty or off-nominal conditions?
Score | Example interpretation
0 — Fail | Small variations would likely make the concept fail.
1 — Poor | Major sensitivity or margin concerns remain.
2 — Adequate | Some margins exist, but key uncertainties are not fully assessed.
3 — Good | Major uncertainties are assessed; margins appear manageable.
4 — Excellent | Key uncertainties and off-nominal cases are assessed with clear margin.
Engineering Expertise
Guiding question: Does the team have enough relevant expertise to develop the concept?
Score | Example interpretation
0 — Fail | Required expertise is not available.
1 — Poor | Major expertise gaps create significant risk.
2 — Adequate | Some expertise exists, but key gaps remain.
3 — Good | Sufficient expertise exists; gaps are manageable.
4 — Excellent | Strong relevant expertise and expert support are available
Design-Process Discipline
Guiding question: Is the concept developed through a disciplined and traceable process?
Score | Example interpretation
0 — Fail | No traceable design process is demonstrated.
1 — Poor | Design decisions are informal or weakly documented.
2 — Adequate | Some structure exists, but traceability is incomplete.
3 — Good | Assumptions, trades, risks, and reviews are mostly documented.
4 — Excellent | Decisions, assumptions, trades, risks, and actions are clearly tracked.

## 2-Design Verification
Purpose: Assess whether there is enough credible evidence to support that the design will perform as intended before implementation.
Boundary: Focus on analysis, models, heritage, reviews, and verification planning before hardware realization. Hardware testing after manufacturing should be assessed under Implementation Verification.
Scoring rule: Use the current evidence and design maturity. Examples are provided to guide judgment, not to limit the evidence raters may consider.
Indicator Overview
Indicator | Guiding question | Example evidence | Score | General meaning
Model-based evidence | Do analyses or simulations support expected design performance? | Performance model, CFD/FEA, thermal/structural analysis, rotordynamic analysis | 0 — Fail | Not demonstrated or unacceptable
Model credibility | Are the models credible enough for current design decisions? | Benchmarking, validation data, uncertainty estimate, correlation with prior tests | 1 — Poor | Major concerns remain
Organizational heritage | Does the organization have relevant prior experience, internal data, or lessons learned from similar design/verification work? | Similar design, TRL, prior test/flight data, reused architecture | 2 — Adequate | Partially supported, but important gaps remain
Verification rigor | Is the verification process traceable and disciplined? | Verification plan, requirement-to-analysis traceability, review records | 3 — Good | Supported with manageable concerns
Verification Expertise | Does the team have enough expertise to perform verification activities? | Verification experience, analysis skills, model validation expertise, review capability | 4 — Excellent | Strongly supported for current maturity
Model-Based Evidence
Guiding question: Do analyses or simulations support expected design performance?
Score | Example interpretation
0 — Fail | No analysis or model supports the design.
1 — Poor | Analysis is too limited to support key design claims.
2 — Adequate | Some analysis exists, but major performance areas are missing.
3 — Good | Key performance areas are analyzed; gaps are manageable.
4 — Excellent | Analyses consistently support expected performance.
Model Credibility
Guiding question: Are the models credible enough for current design decisions?
Score | Example interpretation
0 — Fail | Model credibility is not demonstrated.
1 — Poor | Major concerns exist in model fidelity, assumptions, or uncertainty.
2 — Adequate | Model is useful, but validation or uncertainty treatment is limited.
3 — Good | Model is reasonably credible with manageable limitations.
4 — Excellent | Model is well supported by validation, benchmarking, or prior data.
Organizational Heritage
Guiding question: Is the design supported by relevant prior designs or empirical data?
Score | Example interpretation
0 — Fail | No relevant organizational heritage exists.
1 — Poor | Heritage is weak or not applicable.
2 — Adequate | Some relevant heritage exists, but applicability is limited.
3 — Good | Relevant heritage supports major design/verification decisions.
4 — Excellent | Strong internal heritage directly supports the current design.
Verification Rigor
Guiding question: Is the verification process traceable and disciplined?
Score | Example interpretation
0 — Fail | No clear verification process is defined.
1 — Poor | Verification activities are informal or poorly traced.
2 — Adequate | Some verification planning exists, but traceability is incomplete.
3 — Good | Verification plan and traceability are mostly established.
4 — Excellent | Verification activities, requirements, assumptions, and reviews are clearly traced.
Verification expertise
Guiding question: Does the team have enough expertise to perform verification activities?
Score | Example interpretation
0 — Fail | Required verification expertise is not available.
1 — Poor | Major verification expertise gaps remain.
2 — Adequate | Basic expertise exists, but key gaps remain.
3 — Good | Sufficient expertise exists; gaps are manageable.
4 — Excellent | Strong verification expertise and review support are available.

## 3-Manufacturing
Purpose: Evaluates whether the design can be physically realized into conforming hardware
Boundary: Focus on whether the design can be built into conforming hardware, not whether the design will perform successfully after integration or testing
Scoring rule:
Indicator Overview
Indicator | What it captures | Example evidence | Score | General meaning
Manufacturing and Inspection Capability | Ability to fabricate required geometry, materials, tolerances, surface finish, joining, coating, cleanliness, or special processes. | Machine capability, prototype, manufacturing plan | 0 — Fail | Not demonstrated or unacceptable
As-Built Quality | Whether the manufactured parts meet the specification | Before: similar-part history, inspection capability After: Dimensional inspection report, material record, manufacturing record | 1 — Poor | Major concerns remain
Manufacturing Process Control | Whether manufacturing work is documented, traceable, and controlled. | AS9100/ISO 9001 or equivalent certification, audit result, work record/checklist, drawing revision control, material traceability, problem/rework record. | 2 — Adequate | Partially supported, but important gaps remain
Manufacturing Expertise | Personnel skill, experience, and staffing adequacy for required manufacturing tasks. | Operator qualification, prior similar hardware, supplier heritage, staffing adequacy | 3 — Good | Supported with manageable concerns
|  |  | 4 — Excellent | Strongly supported for current maturity
Manufacturing and Inspection Capability
Guiding question: Can available manufacturing methods produce the parts?
Score | Example interpretation
0 — Fail | No available machine, process, or inspection method can support the required features, material, or tolerances.
1 — Poor | Basic manufacturing is possible, but there is no clear way to produce or inspect key required features.
2 — Adequate | A basic manufacturing and inspection approach exists, but one or more critical features, tolerances, or material requirements remain uncertain.
3 — Good | Available machines and inspection methods can support most required features, materials, and tolerances, with only minor concerns.
4 — Excellent | Manufacturing and inspection capability has been shown on similar hardware or prototype features with comparable requirements.
As-built Quality
Guiding question: Can the manufactured parts meet the specification?
Score | Example interpretation
0 — Fail | The fabricated part fails key dimensions/material requirements.
1 — Poor | There is major concern about meeting the drawing, such as uncertain hole location, unclear material confirmation, or no reliable inspection method.
2 — Adequate | Some evidence supports conformance, but key checks are missing, such as no inspection plan for the hole pattern or inner diameter.
3 — Good | The shop can inspect key dimensions and material; after fabrication, most drawing requirements are verified with only minor closed issues.
4 — Excellent | Dimensional inspection, material record, and acceptance record show the chamber meets all key drawing requirements with no open quality issues.
Manufacturing Process Control
Guiding question: Is the manufacturing work documented, traceable, repeatable, and controlled?
Score | Example interpretation
0 — Fail | No controlled work process exists; the shop relies on informal instructions.
1 — Poor | Some instructions exist, but drawing version, material record, inspection steps, or rework approval are unclear.
2 — Adequate | A work order/checklist exists, but it does not clearly track all key steps, inspections, or problem handling.
3 — Good | The work record tracks the correct drawing, material, machining steps, inspection steps, and any rework.
4 — Excellent | The process is controlled by a formal quality system, with clear drawing control, material traceability, inspection records, and approved handling of problems and rework.
Manufacturing Expertise
Guiding question: Does the manufacturing team have enough expertise to make parts correctly?
Score | Example interpretation
0 — Fail | The team lacks the machining or inspection skills needed for this chamber case.
1 — Poor | The team has general machining experience, but little or no experience with precision chamber/flange hardware.
2 — Adequate | The team can make basic parts, but depends heavily on one person or lacks experience with some critical features.
3 — Good | The team has relevant experience with similar aluminum cylindrical/flange parts and qualified operators or inspectors.
4 — Excellent | The team/supplier has repeated experience making similar rocket/aerospace hardware, with qualified operators, inspectors, and backup staffing.

## 4-Assembly&Integration
Purpose: Evaluates whether the design can be physically realized into conforming hardware
Boundary: Focus on whether the design can be built into conforming hardware, not whether the design will perform successfully after integration or testing
Scoring rule:
Indicator Overview
Indicator | What it captures | Example evidence | Score | General meaning
Assembly and Interface Compatibility | Whether the applicable parts, components, subsystems can be assembled and connected into the intended configuration without introducing unacceptable defects or incompatibilities. | interface control documents; tolerance and fit assessments; alignment, gap, clearance, preload, and torque measurements; cleanliness inspections | 0 — Fail | Not demonstrated or unacceptable
Procedure Readiness | Whether procedures provide sufficient instructions to perform assembly and integration correctly. | work instructions; tooling requirements; torque or preload limits; assembly sequence; contamination controls; MIP/KIP locations; inspection criteria; procedure walkthroughs; trial execution records | 1 — Poor | Major concerns remain
Process Control | Whether assembly and integration activities are configuration-controlled, inspected, documented | traceability; procedures; inspection sign-offs; MIP/KIP records; calibrated-tool records; NCRs | 2 — Adequate | Partially supported, but important gaps remain
Team Expertise | Personnel skill, experience, and staffing adequacy for required assembly and integration tasks. | Qualification and training records; experience and knowledge of component functions and limitations | 3 — Good | Supported with manageable concerns
|  |  | 4 — Excellent | Strongly supported for current maturity
Assembly and Interface Compatibility
Guiding question: | Can the system be assembled and connected correctly without creating defects or interface problems?
Score | Example interpretation
0 — Fail | Parts cannot be installed without interference, a critical fluid connection is incompatible, or the required electrical connector has an incorrect pin configuration.
1 — Poor | Hardware can only be assembled after unapproved machining, or an interface requires temporary rewiring that is not reflected in the released configuration.
2 — Adequate | Most parts fit correctly, but a critical gap or preload has not been measured; mechanical interfaces have been checked, but the fluid interface has not yet been mated.
3 — Good | Required fit, alignment, torque, cleanliness, continuity, and leak checks are acceptable, with one minor documentation discrepancy awaiting closure.
4 — Excellent | Multiple representative builds were completed using released processes, and records confirm acceptable fit, alignment, preload, cleanliness, interface mating, continuity, and leak performance.
Procedure Readiness
Guiding question: | Are the procedures complete, current, and usable enough to guide the work and prevent critical errors?
Score | Example interpretation
0 — Fail | The procedure references an earlier hardware configuration or directs personnel to use an incorrect installation sequence.
1 — Poor | Torque limits and cleanliness requirements are not specified, and technicians rely on verbal guidance from one experienced engineer.
2 — Adequate | The procedure defines installation steps but does not clearly identify MIP/KIP locations, discrepancy response, or acceptable alignment limits.
3 — Good | The procedure identifies the correct hardware configuration, installation sequence, calibrated tools, torque limits, cleanliness controls, and inspection sign-offs.
4 — Excellent | A representative trial identified sequencing and access issues; the procedure was updated, reviewed, and successfully used during subsequent assembly.
Process Control
Guiding question: | Is the work controlled, inspected, recorded, and formally closed before release?
Score | Example interpretation
0 — Fail | Part serial numbers are unknown, required inspections were not recorded, or personnel cannot determine which drawing revision was used.
1 — Poor | Assembly travelers contain missing sign-offs, or an out-of-tolerance condition was corrected informally without an NCR or approved disposition.
2 — Adequate | Most steps are signed, but some tool-calibration evidence, installed-part traceability, or deviation closure is incomplete.
3 — Good | The build record identifies installed parts, measurements, responsible personnel, tool status, and closed NCRs, with one noncritical record correction pending.
4 — Excellent | The final record reconstructs the complete build history, including serialized parts, procedure revisions, calibrated tools, inspection results, deviations, and approved dispositions.
Team Expertise
Guiding question: | Does the team have the know-how to assemble and integrate the system successfully?
Score | Example interpretation
0 — Fail | No assigned personnel are qualified to perform a critical joining process or handle contamination-sensitive hardware.
1 — Poor | Personnel can follow routine steps but do not understand thermal-fit installation, preload control, interface limitations, or abnormal-condition indicators.
2 — Adequate | Most technicians are capable, but an external specialist is required for sensitive connector mating or rotor alignment, and backup coverage is limited.
3 — Good | Qualified personnel have experience with similar hardware, complete a pre-job briefing, understand contamination and alignment requirements, and know when to stop the work.
4 — Excellent | The team has successfully completed several similar builds, rehearses critical steps, maintains backup expertise, and uses previous anomalies and lessons learned to improve execution.

## 5-Impl Verification
Purpose: Evaluates whether the manufactured system meets its requirements
Boundary: Focus on verified things, verification methods, team expertise, and verification process rigor
Scoring rule:
Indicator Overview
Indicator | What it captures | Example evidence | Score | General meaning
Verification coverage | Whether critical requirements can be verified | Requirement-verification matrix, inspection plan, qualification and acceptance plans, critical inspection points | 0 — Fail | Not demonstrated or unacceptable
Verification Effectiveness | Whether methods, facilities, test configuration, conditions, and measurement systems can demonstrate real conditions | Loads and environments, calibrated instrumentation, maintenance records, measurement accuracy, leak test | 1 — Poor | Major concerns remain
Verification Expertise | Whether the team has the knowledge and experience to carry out verification activities correctly | Relevant experience, training, prior similar verification activities | 2 — Adequate | Partially supported, but important gaps remain
Verification Rigor | How rigorous are the activities being carried out | Approved procedures, witness points, data reviews, anomaly/NCR report | 3 — Good | Supported with manageable concerns
|  |  | 4 — Excellent | Strongly supported for current maturity
Verification Coverage
Guiding question: Have the applicable functional, performance, physical, interface, and safety requirements been addressed using appropriate verification activities?
Score | Example interpretation
0 — Fail | No defined verification scope exists, or critical requirements have not been assigned a verification activity.
1 — Poor | A small portion of the requirements has been addressed, but several critical functions, interfaces, performance characteristics, or safety requirements remain unverified.
2 — Adequate | Major requirements have verification activities, but important gaps remain in areas such as interfaces, off-nominal behavior, workmanship, or safety-critical characteristics.
3 — Good | Critical requirements and most other applicable requirements are covered by inspection, analysis, demonstration, or testing. Only minor gaps remain, and they are identified.
4 — Excellent | Applicable requirements are comprehensively and traceably connected to suitable verification activities. Critical functions, performance, interfaces, physical characteristics, and safety requirements are addressed, and identified gaps have been resolved.
Verification Effectiveness
Guiding question: Are the selected verification methods, conditions, configurations, facilities, and measurements capable of revealing relevant deficiencies and demonstrating requirement compliance?
Score | Example interpretation
0 — Fail | The selected methods or setup cannot demonstrate compliance with the requirements or detect the relevant deficiencies. Results are not technically usable.
1 — Poor | Verification activities provide limited information because of major weaknesses in method suitability, test conditions, configuration, facility capability, or measurement accuracy.
2 — Adequate | The verification approach can evaluate the primary behavior, but important limitations remain in fidelity, measurement capability, boundary conditions, configuration, or uncertainty.
3 — Good | Verification methods and setups are suitable for the applicable requirements. Conditions, configurations, and measurements are sufficiently representative, with only minor understood limitations.
4 — Excellent | Verification methods and setups have demonstrated capability to detect relevant deficiencies and establish compliance. Important uncertainties, limitations, and differences from operational conditions are characterized and appropriately addressed.
Verification Expertise
Guiding question: Does the verification team have the knowledge, experience, and staffing needed to plan, conduct, and interpret the required verification activities?
Score | Example interpretation
0 — Fail | The team lacks the knowledge or personnel required to conduct and interpret the verification activities. Critical responsibilities are unassigned.
1 — Poor | The team has limited relevant experience and depends heavily on a small number of individuals or external support. Important technical expertise is missing.
2 — Adequate | The team can perform routine verification activities, but expertise or staffing gaps remain for complex, specialized, or safety-critical work.
3 — Good | The team has relevant experience and sufficient staffing to plan, conduct, review, and interpret the required verification activities. Appropriate specialists are available when needed.
4 — Excellent | The team has demonstrated expertise from comparable hardware or verification programs, sufficient depth across critical disciplines, and the ability to recognize unexpected behavior, evaluate anomalies, and challenge questionable results.
Verification Rigor
Guiding question: Are verification activities planned, executed, reviewed, documented, and closed out through controlled and traceable processes?
Score | Example interpretation
0 — Fail | Verification is conducted informally without controlled procedures, configuration records, reliable data records, or documented disposition of problems.
1 — Poor | Some procedures and records exist, but execution is inconsistent. Configuration, data, deviations, or anomalies are poorly controlled.
2 — Adequate | Verification activities generally follow documented processes, but important gaps remain in procedure approval, configuration traceability, data review, deviation control, or anomaly closure.
3 — Good | Verification follows approved procedures using controlled configurations and traceable records. Results are reviewed, deviations are documented, and anomalies are investigated and closed with appropriate corrective action or retesting.
4 — Excellent | Verification processes are consistently and demonstrably controlled. Appropriate readiness reviews, independent checks or witnessing, configuration control, data-quality review, deviation approval, anomaly resolution, and closure evidence are applied to critical activities.

## 6-Op Setup
Purpose: Evaluates whether all systems are reday for operation before excution
Boundary: Is the system placed in the correct initial state for the execution?
Scoring rule:
Indicator Overview
Indicator | What it captures | Example evidence | Score | General meaning
Mission Configuration Readiness | Whether the vehicle, payload, software, parameters, interfaces, and consumables are in the approved mission configuration | Configuration records, software version records, parameter lists, interface status, system status reports | 0 — Fail | Not demonstrated or unacceptable
Operational Support Readiness | Whether ground systems, facilities, communications, power, monitoring, and safety support are available and functioning | Ground-system status, equipment checkout, communication checks, facility status, power-system, safety-system, external service confirmations. | 1 — Poor | Major concerns remain
External Condition Criteria | Whether allowable limits and go/no-go criteria are defined for weather, range, launch-site, airspace, maritime, and other external conditions relevant to the operation. | Weather limits, wind limits, launch or test commit criteria, range requirements, airspace or maritime clearance requirements, hazard-area criteria, site constraints, mission timing windows, hold/scrub criteria | 2 — Adequate | Partially supported, but important gaps remain
Setup Procedure Control | Whether setup steps, inspections, verification points, documentation, and handover criteria are complete and controlled | Approved procedures, revision records, procedure walkthroughs quality | 3 — Good | Supported with manageable concerns
Setup Team Readiness | Whether the personnel have the knowledge, experience, and staffing needed to perform and verify the setup correctly | Qualification records, role assignments, communication plans, rehearsals, contingency drills | 4 — Excellent | Strongly supported for current maturity
Mission Configuration Readiness
Guiding question: | Are the hardware, software, parameters, interfaces, and system states correctly configured for this operation?
Score | Example interpretation
0 — Fail | The actual system configuration is unknown, incorrect, or inconsistent with the approved mission configuration. Critical configuration items have not been confirmed.
1 — Poor | Some configuration items have been checked, but major uncertainties remain in hardware, software, parameters, interfaces, consumables, or system state.
2 — Adequate | The primary mission configuration has been established, but some important items remain unconfirmed, unresolved, or supported by incomplete records.
3 — Good | Hardware, software, parameters, interfaces, consumables, and system states match the approved configuration. Only minor documented issues remain, with understood disposition.
4 — Excellent | The complete mission-specific configuration is confirmed through controlled and traceable records. Open work, deviations, waivers, and temporary configurations have been reviewed and formally accepted.
Operational Support Readiness
Guiding question: | Are the ground systems, facilities, communications, power, monitoring, safety systems, and other operational support available and functioning?
Score | Example interpretation
0 — Fail | Critical support systems or services are unavailable, nonfunctional, or incapable of supporting the operation.
1 — Poor | Some support systems are available, but major capability, availability, communication, facility, monitoring, or safety gaps remain.
2 — Adequate | Essential support is generally available, but important limitations, temporary arrangements, unresolved faults, or insufficient backup capability remain.
3 — Good | Required support systems and services have been checked and are functioning for the planned operation. Minor limitations are understood and controlled.
4 — Excellent | All required support systems, facilities, services, and safety resources are confirmed ready under the planned operating configuration. Critical dependencies and backup arrangements have also been demonstrated or confirmed.
External Condition Criteria
Guiding question: | Are clear and appropriate allowable limits or go/no-go criteria defined for the external conditions that could affect the operation?
Score | Example interpretation
0 — Fail | Critical external conditions have no defined allowable limits or go/no-go criteria.
1 — Poor | Some limits or criteria exist, but major external conditions are missing, unclear, or based mainly on informal judgment.
2 — Adequate | Criteria are defined for most important external conditions, but some limits, rationale, monitoring methods, or decision criteria remain incomplete.
3 — Good | Clear criteria are defined for all relevant external conditions and can support consistent go/no-go decisions. Monitoring and acceptance methods are established.
4 — Excellent | Comprehensive and well-supported criteria are defined for all relevant external conditions. Limits, margins, monitoring methods, and hold/scrub or contingency criteria are clearly established and verified.
Setup Procedure Control
Guiding question: | Are the nominal and emergency procedures complete, validated, and consistent with the actual system configuration?
Score | Example interpretation
0 — Fail | Required procedures do not exist, are unusable, or do not match the current system and operation.
1 — Poor | Basic procedures exist, but major gaps remain in sequencing, responsibilities, decision criteria, contingency actions, or configuration alignment.
2 — Adequate | Nominal procedures are generally usable, but some important steps, interfaces, contingency cases, approval records, or validation activities remain incomplete.
3 — Good | Nominal and applicable contingency procedures are complete, approved, current, and aligned with the operational configuration. Minor issues remain but do not prevent safe use.
4 — Excellent | Procedures have been validated through appropriate walkthroughs, simulations, or rehearsals. Roles, interfaces, hold points, decision criteria, abort actions, and contingency responses are clearly defined and confirmed usable.
Setup Team Expertise
Guiding question: | Is the team trained, sufficiently staffed, and prepared to conduct the operation and respond to contingencies?
Score | Example interpretation
0 — Fail | Critical roles are unfilled, personnel are unqualified, or the team cannot safely conduct the planned operation.
1 — Poor | Major gaps exist in training, staffing, role definition, communication, coordination, or contingency preparation.
2 — Adequate | The team can conduct routine activities, but important limitations remain in experience, staffing depth, coordination, rehearsal, or off-nominal preparation.
3 — Good | Required roles are staffed by trained personnel. Responsibilities, authority, communication paths, and coordination arrangements are clear, with only minor concerns.
4 — Excellent | The team has demonstrated readiness through relevant simulations, rehearsals, or comparable operations. Critical roles have sufficient depth, and the team is prepared for both nominal activities and credible contingencies.

## 7-Op Execution
Purpose: evaluate whether the team and op system are ready to be executed
Boundary: Once the execution begins, can we observe it, control it, and execute it as planned?
Scoring rule:
Indicator Overview
Indicator | What it captures | Example evidence | Score | General meaning
Operational Observability | Can the team observe the system states, conditions, and anomalies needed to manage the test? | Telemetry and sensor coverage; camera coverage; data-acquisition; critical system states and abnormal conditions can be detected | 0 — Fail | Not demonstrated or unacceptable
Operational Controllability | Can the team issue necessary commands and take effective intervention, shutdown, or abort actions? | Command and control; valve and actuator command tests; shutdown, emergency-stop, hold, and abort demonstrations | 1 — Poor | Major concerns remain
Execution Procedure Readiness | Is there a complete and usable plan for nominal, off-nominal, and emergency execution? | Approved procedures, abort criteria | 2 — Adequate | Partially supported, but important gaps remain
Team Execution Readiness | Is the team trained, staffed, coordinated, and prepared to execute the plan and respond to changing conditions? | role assignments, communication plans, rehearsals, contingency drills | 3 — Good | Supported with manageable concerns
|  |  | 4 — Excellent | Strongly supported for current maturity
Operational Observability
Guiding question: | Can the team observe the system states, conditions, and anomalies needed to manage the test?
Score | Example interpretation
0 — Fail | Critical system states cannot be monitored, or monitoring capability has not been established. The team cannot reliably determine whether the system is operating safely or as expected.
1 — Poor | Basic monitoring is available, but major gaps remain in critical sensors, telemetry, cameras, alarms, data displays, or communication links. Important anomalies may not be detected.
2 — Adequate | The primary system states can be monitored, but important limitations remain in coverage, data quality, alarm definition, communication reliability, or visibility of off-nominal conditions.
3 — Good | Critical system states, operating conditions, and relevant anomalies can be monitored through checked telemetry, displays, alarms, cameras, and communication links. Only minor, understood limitations remain.
4 — Excellent | Monitoring capability has been demonstrated end to end under representative nominal and off-nominal scenarios. Critical conditions can be detected, distinguished, and communicated within the required time, with appropriate backup coverage for critical information.
Operational Controllability
Guiding question: | Can the team issue necessary commands and take effective intervention, shutdown, or abort actions?
Score | Example interpretation
0 — Fail | Critical commands or protective actions are unavailable, unverified, or unable to place the system in a safe state.
1 — Poor | Basic commands are available, but major gaps remain in command paths, response confirmation, shutdown, isolation, emergency stop, or abort capability.
2 — Adequate | Normal control functions are generally available, but important limitations remain in response time, command confirmation, backup paths, interlocks, or off-nominal intervention capability.
3 — Good | Required commands, holds, shutdowns, isolation actions, and abort functions have been checked and can be executed within the required time. Minor limitations are understood and controlled.
4 — Excellent | Control and intervention capability has been demonstrated end to end under representative nominal and off-nominal scenarios. Critical actions are timely, confirmed, reliable, and supported by appropriate backup or fail-safe provisions.
Execution Procedure Readiness
Guiding question: | Is there a complete and usable plan for nominal, off-nominal, contingency, and emergency execution?
Score | Example interpretation
0 — Fail | No usable execution procedure exists, or the procedure is inconsistent with the current system and planned operation.
1 — Poor | A basic sequence exists, but major gaps remain in operating steps, roles, expected values, decision points, hold criteria, abort actions, or off-nominal responses.
2 — Adequate | The nominal sequence is generally usable, but important parts remain incomplete, unclear, unvalidated, or poorly coordinated across teams. Some contingency or emergency conditions are not adequately addressed.
3 — Good | The procedure is approved, current, and aligned with the operational configuration. Nominal steps, limits, callouts, hold points, decision criteria, and applicable off-nominal responses are defined. Only minor issues remain.
4 — Excellent | The procedure has been validated through appropriate walkthroughs, dry runs, or simulations. Nominal and credible off-nominal scenarios are addressed, responsibilities and decision authority are clear, and the procedure has demonstrated usability by the operational team.
Team Execution Readiness
Guiding question: | Is the team trained, sufficiently staffed, and prepared to conduct the operation and respond to contingencies?
Score | Example interpretation
0 — Fail | Critical control-room roles are unfilled or personnel lack the qualifications needed to safely conduct the operation.
1 — Poor | Major gaps exist in training, staffing, role clarity, communication, system understanding, or preparation for off-nominal conditions.
2 — Adequate | The team can perform routine nominal activities, but important limitations remain in staffing depth, coordination, decision authority, rehearsal, anomaly response, or contingency preparation.
3 — Good | Required roles are staffed by trained personnel. Responsibilities, communication paths, decision authority, and escalation processes are clear. The team has completed relevant rehearsals, with only minor concerns remaining.
4 — Excellent | The team has demonstrated coordinated performance through representative nominal and off-nominal simulations or comparable operations. Personnel can interpret system information, communicate effectively, and make timely hold, shutdown, abort, or emergency decisions.